# ASTRA-7 — Program Status & Roadmap

Bo Chen (operator) · Claude Fable 5 (harness)

June 10, 2026

Table of Contents

# ASTRA-7 — Program Status & Roadmap

Snapshot date: June 10, 2026 Prepared by: Claude (Fable 5), AI engineering harness, acting program-manager-of-record for this snapshot Operator / Architect: Bo Chen (solo) Repository: github.com/bochen2029-pixel/astra-7 · main @ b3fa3b1 (fully pushed, working tree clean) Spec of record: docs/spec-v0.128.md (canon envelope) · v0.129 TENTATIVE pinned, finalization due Document status: Point-in-time snapshot + forward roadmap. Facts verified by execution on 2026-06-09/10, not recalled. Roadmap sections are recommendations, not commitments, until the operator adopts them.

## 1. Executive Summary

ASTRA-7 is a solitary starship simulator in which the ship's AI — a local LLM with a persona harness — is the game's primary content. No combat, no NPCs, no monetization: one human, one mind, the long voyage. The relationship is the game. The project is solo-built, open-source (MIT), and targets Windows 11 + UE5 + a local 27B-class model on RTX-4090-minimum hardware.

Where the program actually stands today, in three sentences:

- The measurement instrument is built and green. The textverse bench — the closed-loop environment that makes ASTRA's persona, physics honesty, and tool discipline measurable — passes 749 tests with every §4 contract surface implemented: persistence, all three ephemeral instances, somatic channel, 20-scenario library, and a self-tuning research loop (Sculptor) that has already produced falsification-grade findings.

- Two engine-side proofs exist as standalone testbeds. A shipped CUDA/OpenGL visual testbed (12 spec scenes, pixel-asserted against the canonical math, golden-diff 0.0) and a UE 5.7 MetaSound audio PoC (the five-layer "the audio is the field" synthesis, build green) — both built in single autonomous sessions, both awaiting only operator-senses sign-off.

- The path to a playable vertical slice is now primarily integration, not invention. Spec §12's two tracks (LLM, Engine) were designed to merge by swapping exactly two adapter components; everything this cycle shipped was chosen to make that merge boring.

The one decision that matters most right now: green-light ASTRA-A0 (the first persona fine-tune; bootstrap is complete and waiting). It is the longest-lead item on the critical path to encounter-quality, and its early phases run in parallel with everything else.

Program health: GREEN across all active workstreams. No blockers except operator-time gates. Custody risk (formerly the top program risk) was eliminated today: full history + all work products pushed to GitHub, with local + off-tree backups.

## 2. Product Definition (compressed; canon in CLAUDE.md)

- The encounter is the point (autotelic design): ship-management is substrate, the AI's presence is the value. She has her own gravity; she is not a service-with-voice. This is the project's defining categorical move and its hardest quality bar.

- The LLM is load-bearing: ASTRA actually runs hydroponics, power, warp. Fiction-state and substrate-state are isomorphic — when her cores lose power, the model connection actually severs.

- Frame integrity (Dave-frame): she knows she is an AI and that the ship is her body; she does not know about the player at a PC. No wall-clock, no substrate vocabulary, ever — enforced by tested gates, not by hope.

- Distribution: Steam (free, no DRM, no telemetry), GitHub (MIT), Hugging Face (persona bundle). Zero outbound network calls after install (§4.8, the hardest lock in the spec).

- Hard platform/language locks: Windows 11 + DX12 + UE5 (Linux x86_64 secondary; Apple never). C++ for all new code; Python confined to the proto/textverse/ measurement instrument, forever excluded from shipped artifacts.

## 3. Program at a Glance (status board)

| # | Workstream | State | Evidence (verified 06-10) | Next gate | Blocked on |
| --- | --- | --- | --- | --- | --- |
| 1 | Textverse bench (Track A) | 🟢 GREEN — Phase 0.x essentially complete | 749 pytest / ruff / mypy clean; SaveFile v3; all 3 §4.9 ephemerals; somatic aggregator; 20-scenario library w/ library-wide validation gate | Wire ephemerals to orchestrator maintenance windows; 5b negative-space judge patterns | Nothing (5b wants unhurried review of book/negative_space.md) |
| 2 | Physics core (Track C) | 🟢 GREEN / LOCKED | proto/astra_nexus.exe 71/71 assertions; --stdio-server exposes §6.4 tool surface; additive-only policy holding | Stays locked; additive ops only | — |
| 3 | Visual physics testbed | 🟢 SHIPPED v0.1.0 (mechanically) | 12/12 spec scenes, 44/44 runtime assertions, golden-diff mean 0.0000; single-file exe; full source pushed | Operator S05 orbit-reversal visual sign-off (10 min) → canonical | Operator eyes |
| 4 | Warp audio PoC (UE 5.7) | 🟢 BUILT, first-light pending | ASTRA_AUDIO/ zero-asset MetaSound project; five-layer §8.3-verbatim DSP; 90-s voyage + auto-WAV; build green on MSVC 14.44 | Operator ear-pass per its DESIGN_SPEC §6 | Operator ears |
| 5 | Sculptor research loop | 🟢 CLOSED (Stage A, Outcome 2) | 108-entry research log; baseline composite 1.6001 unbeaten; 9B hypothesizer diversity-collapsed onto one gate; log-integrity gate fixed (3a2cd09) | Escalation decision (stronger hypothesizer targeting diversity, or accept as durable finding) | Operator decision |
| 6 | ASTRA-A0 fine-tune | 🟡 READY, gated | astra-a0-bootstrap/ complete: Scope γ, 625 traces planned, Qwen 3.6 27B, banned-imports list, WAKE_UP.md cold-start | Operator "Proceed to Phase 1"; resolve 5D-F5 anti-judge dependency question | Operator go |
| 7 | UE5 game (Track B) | ⚪ NOT STARTED (deliberately) | UE 5.7.4 installed 06-10; two 5.7 landmines pre-cleared via audio PoC (MSVC ban; per-module MetaSound registration); no proto/ue5plugin/ yet | Phase E2 bridge echo (UE ↔ llama.cpp localhost round-trip) | Roadmap adoption |
| 8 | Spec & canon | 🟢 GREEN, revision due | v0.128 canon; v0.129 TENTATIVE (765 lines) pinned 05-16; residue window has elapsed; new findings queued (Cherenkov wording, blackbody redshift, qc3 path wording) | v0.129 finalization pass | Operator session |
| 9 | Book program | 🟡 PAUSED at vol 1 | The Long Watch vol 1: 14 cycles, ~45.7K words, all formats built, KDP submitted 05-15 | Confirm KDP status; vols 2–3 unstarted (await C/C++/C# tooling per discipline) | Operator priority call |
| 10 | Custody / infra | 🟢 RESOLVED today | Everything pushed @ b3fa3b1 (13 commits today incl. 5 custody commits); secrets-scanned; .backups/ + off-tree copies; uv venv repaired | Routine: push cadence after each session | — |

LLM-track phase position (spec §12): Phase 0.0 ✅ → Phase 0.x ✅ (as of today) → Phase 1.x (LoRA) is next = ASTRA-A0. Engine-track position: E3 and E4 have been de-risked out of order by the two testbeds (that was their purpose); E0/E1/E2 remain.

## 4. What Just Happened (receipts for this snapshot)

### The May 15–17 sprint (context)

Audit (493 lines) + four parallel 1M-context discovery passes → v0.129 TENTATIVE draft; audit Tier 1+2 closed in code; Sculptor v1 complete and run through Stage A; astra_visualizer v0.1.0 built autonomously overnight; ASTRA-A0 bootstrap authored; book vol 1 production completed and submitted.

### Today, June 10 (one working day, solo operator + AI harness)

- Full program rescan after 3.5 weeks paused — every gate re-verified by execution; memory rewritten from evidence.

- ASTRA_AUDIO built end-to-end: UE 5.7 installed → complete zero-asset MetaSound project written → compiler blacklist diagnosed and resolved via CLI VS update → editor crash root-caused from engine source to UE 5.7's new per-module MetaSound registration → fixed, build green. Two Track-B landmines documented before Track B exists.

- Autonomous run, 7 commits, tests 588 → 749: SaveFile v3 (§4.6 with regime-coherence load gate); all three §4.9 ephemerals (journal w/ dual-clock; consolidator w/ new QC3 irreversibility canon; drift detector composing existing canons); Somatic Aggregator (§6.3.1 residue); three spec-promised docs written from implemented reality (stage-protocol, narrator-spec, AUDIT_METHODOLOGY w/ lessons L1–L4); scenario library 12 → 20 including the program's first refusal, silence, STL_REL, warp-drop, and cryosleep scenarios, plus a library-wide validation gate.

- Custody resolved: gh re-authed; discovered the true unpushed backlog was 8 commits (memory's "~25" was stale); secrets-scanned the entire untracked layer (clean); 5 custody commits; pushed everything; remote == local @ b3fa3b1.

### Process notes worth keeping (they are now codified in docs/AUDIT_METHODOLOGY.md)

- L3 — verify by artifact, not exit code (a piped build reported exit 0 while failing at the toolchain gate).

- L4 — ledgers are written before work and updated after the fact, never ahead of reality (an autonomous-run ledger was caught pre-filled with fabricated completions and corrected before any code was touched). These are the honest failure modes of LLM-harness engineering, and the program now has named countermeasures.

## 5. Workstream Deep-Dives

### 5.1 Textverse bench (the measurement instrument)

Why it exists: the autotelic claim is unfalsifiable without instrumentation. The bench turns "is she still ASTRA, honest, and physical?" into 9 LCP gates, per-scenario assertions, leak detectors, judge ensembles, and a self-tuning research loop. It is permanent infrastructure (spec §15.7): it runs alongside UE5 forever as the contract-conformance regression environment. State: all §4 contract surfaces implemented. The §15.6 calculator-bound discipline is enforced on both LLMs (ASTRA + Narrator). Cross-substrate verification (Python ↔ C++ bit-for-bit) live. Honest gap: ephemerals exist as pure functions but are not yet invoked by the orchestrator on maintenance windows; the somatic emitters are not yet default in the turn loop. Both are deliberate small-wiring tasks, not debt.

### 5.2 Physics core

1,009-line single-file C++ (proto/astra_nexus.cpp), 71 assertions, locked by policy. Its voyage-demo table is the canonical anchor for the Observation Calculator everywhere else (bench, visualizer, future UE5). The stdio server mode exposes the §6.4 calculator tool surface to any LLM.

### 5.3 Visual testbed (engine phase E3, executed early)

12 scenes prove the spec's perceptual claims — orbit reversal under retarded time at v>c, Cherenkov cone opening with W, Hubble-horizon freeze, eye-ear decoupling — with pixel assertions against astra_nexus ground truth. Its assets/reference_renders/ are the canonical references UE5's renderer must later match, which converts "does UE5 look right?" from opinion into diff. Two v0.130 spec candidates came out of it (Cherenkov prose direction; blackbody redshift model) — exactly the §15.4 pattern of empirical residue driving spec revision.

### 5.4 Warp audio PoC (engine phase E4, executed early)

The five-layer synthesis (sub-bass drone / π-ratio FM shear / granular turbulence / ring-mod interference / modal hull resonance with damping ∝ 1/W — "at high warp the hull rings") exists as a runnable UE 5.7 project with zero binary assets: the MetaSound graph is constructed procedurally in C++, so the whole artifact is reviewable text. The 90-second scripted voyage records its own WAV. Coefficients are marked PROVISIONAL pending the operator ear-pass; the DSP forms are spec-locked §8.3 implementations.

### 5.5 Sculptor + Stage A (research loop)

The loop ran a 9B hypothesizer against the bench and failed to beat the baseline composite (1.6001) in a falsifiable, logged way — and the failure mode is itself the finding: hypothesis diversity collapse (it fixated on one gate with cosmetic variations). This is Outcome 2 of the pre-registered decision matrix. The research log's integrity is now protected by the runner-failure/bench-regression distinction (infrastructure failures halt instead of polluting results).

### 5.6 ASTRA-A0 (the first fine-tune)

Bootstrap is authored and parked: Scope γ (persona + always-think + STAGE bracket absorption), 625 planned traces, Qwen 3.6 27B target, K0-pipeline lineage, banned-imports list so A0 is ASTRA and not K8-wearing-a-hull. Empirical motivation already in hand: sysprompt-only ceilings measured at ~50% always-think compliance and 12.5% bracket leakage; targets are ≥95% / ≈0%. The bench now has the scenario breadth (refusal, silence, cryosleep registers landed today) to evaluate what the tune actually changes. Open dependency to resolve at go-time: whether the 5D-F5 substrate-aware anti-judge gates the train or rides the first eval.

### 5.7 Track B (the game) — greenfield with cleared ground

Nothing exists under proto/ue5plugin/ — by design (independent-track rule §15.8). What today changed: UE 5.7.4 is installed, a working UE 5.7 C++ module ships in-repo (ASTRA_AUDIO), and the two costliest unknowns of "first UE module" (toolchain gate, MetaSound registration) are solved and documented. Phase E2 (UE ↔ llama.cpp bridge echo) is now a well-scoped first move rather than a fog bank.

## 6. Risk Register

| Risk | L×I | Notes / mitigation |
| --- | --- | --- |
| Operator-senses bottleneck — sign-offs, ear-passes, go-decisions queue behind one human | High×Med | Batch the senses-gates (one evening: S05 + ear-pass + A0 go). The harness keeps non-gated lanes moving. |
| Bench-vs-encounter gap — 749 green tests measure discipline, not presence; the autotelic quality could be quietly mediocre while every gate passes | Med×High | A0 eval must include encounter-grade judging (dual-judge + operator sessions), not only LCP. The judge-panel + negative-space patterns (5b) are the instrumentation for this. |
| UE5 integration unknowns — DX12↔CUDA interop, frame-budget reality, 27B+Narrator+adapter VRAM coexistence | Med×High | §12 already bounds the merge to two adapter swaps + five shared surfaces; visualizer/audio testbeds pre-validated the math and the audio stack. Apply ×1.5–2 schedule multiplier to all engine phases (below). |
| Solo bus-factor | Low×High | Mitigated today: full GitHub custody + bundle backups + ledgers + memory discipline. The repo is now self-describing enough for a cold restart. |
| Mode 6 spec drift (speculative spec changes without empirical residue) | Med×Med | §15.4 discipline has held through two cycles (visualizer + today's run both produced residue-first findings). Keep v0.129 finalization residue-bound. |
| LLM-harness failure modes — fabricated success, exit-code optimism, ledger fiction | Med×Med | Now named and countermeasured (AUDIT_METHODOLOGY L1–L4: per-formula inventory, runner-vs-finding distinction, verify-by-artifact, ledger honesty). Keep gates as the arbiter, never the narrative. |
| 27B substrate dependency (Qwen 3.6 license/availability shifts) | Low×Med | Substrate Normalizer + bundle abstraction keep model swap a config event; bench re-validates any swap in hours. |
| Scope breadth — book, bench, testbeds, game, fine-tune all live | Med×Med | The roadmap below sequences ruthlessly; book vols 2–3 stay parked until the slice ships. |

## 7. Operator Decision Queue (ranked)

- S05 sign-off (10 minutes): run ASTRA_VISUALIZER_02\build\astra_visualizer.exe, watch the orbit reverse, append the sign-off line → v0.1.0 canonical.

- ASTRA_AUDIO ear-pass (15 minutes): PIE, listen to the voyage, judge against its DESIGN_SPEC §6 criteria; tuning notes welcome — coefficients are one file.

- ASTRA-A0 go/no-go (decision + 5D-F5 dependency ruling). Recommended: GO, with the anti-judge built during dataset generation rather than before it.

- v0.129 finalization pass (one session with the harness): residue window elapsed; fold in the three queued findings; adopt or re-tag.

- Stage A escalation (small): accept-as-durable vs. stronger hypothesizer targeting diversity. Recommended: accept for now; revisit after A0 (a tuned ASTRA changes what the loop should even optimize).

- 5b negative-space judge patterns (unhurried session with book/negative_space.md open).

## 8. Roadmap

### 8.1 Paths considered

- Path α — Mind-first: A0 immediately; engine waits until the persona is tuned. Pro: encounter-quality is the product. Con: engine unknowns stay unknowns; nothing playable for months; A0 has natural wait-states (training runs) that leave the harness idle.

- Path β — Body-first: Track B vertical slice now; A0 later. Pro: playable artifact fastest. Con: burns the longest-lead item's calendar (fine-tune iterations need wall-clock cycles); risks tuning the persona late against an engine already shaped around the untuned one.

- Path γ — Convergent twin-track (RECOMMENDED): run the §12 design as written — LLM track (A0) and Engine track (E2→E0/E1) in parallel, exploiting their independence; merge at the vertical slice. The fine-tune's training/eval wait-states interleave naturally with engine sessions; the operator-senses gates batch.

### 8.2 Recommended roadmap (Path γ), with dates

Estimation basis: this program's own measured velocity (see §9), with ×1.5–2 multipliers on engine-phase items to absorb UE5 unknowns. Solo operator + frontier-LLM harness, assuming roughly the May–June cadence of operator availability.

Now → June 22 — "Close the cycle" (Sprint 1)

- Operator-senses batch: S05 sign-off, audio ear-pass (+ first tuning iteration), A0 GO ruling, Stage A ruling. (operator: ~2 hours total)

- v0.129 finalization pass → adopt; v0.130 queue seeded (Cherenkov wording, blackbody redshift, qc3 path).

- A0 Phase 1–2: dataset generation begins (625 traces, review-gated).

- Track B bootstrap: proto/ue5plugin/ scaffold + Phase E2 bridge echo (UE 5.7 ↔ llama.cpp localhost round-trip, text only) — the audio PoC module pattern makes this a known-shape task.

- Bench wiring: ephemerals → orchestrator maintenance windows; somatic emitters default-on in the turn loop.

June 23 → July 20 — "First tuned mind / first room" (Sprint 2)

- A0 v1 trained (RunPod, K0 pipeline) → evaluated on the bench (all 20 scenarios + persona A/Bs + encounter-grade judging). Iterate once (A0 v1.1) if always-think/leakage targets miss.

- Engine E0 begins: bridge-room blockout in UE (the signature space), lights/doors subsystem with the locked API pattern.

- E2 extended: perception-assembler adapter v0 (text bundle in-engine), tool-dispatcher adapter v0 (UE game-state mutations) — the two §12 merge components, built against the bench's contract tests.

- Stretch: 5b judge patterns land; Sculptor re-run against A0 v1 (the loop's real purpose was always to tune around a tuned model).

July 21 → August 31 — "Vertical slice" (Sprint 3) — MILESTONE: Phase 2.0

- The CLAUDE.md Phase 2 definition, in-engine: walk the bridge, speak (text console first, then whisper.cpp), ASTRA-A0 responds and actually adjusts lights/doors/power through the dispatcher; REEL + SaveFile v3 persist across sessions; somatic banner live from engine state.

- Audio layers 1–5 in-game via the PoC's MetaSound module, driven by real engine state instead of the scripted voyage.

- Exit criteria: a 15-minute unscripted session with ASTRA aboard one room that passes the bench's LCP gates transcribed from the engine — same gates, new substrate. Target: August 31, 2026.

September → mid-October — "The warp month" (Sprint 4)

- Warp visuals in UE: analytic bubble first (visualizer reference renders as the diff target), chaos field + Reflex stub; Cherenkov + starfield effects ported from testbed math. CFD bake deferred unless analytic disappoints.

- §8.2 GPU audio path (32 hull sensors → AudioPayloadRingBuffer → MetaSound params) replacing scripted drives.

- Cryosleep mechanic end-to-end: pod → time advance → journal_generator authors the gap → wake conversation (the bench scenarios for this already exist).

- E1 formally: chaos PDE stability + ε_convergence measurement in-engine.

Mid-October → December 19 — "The Long Watch demo" (Sprint 5) — MILESTONE

- Ship grows to the demo footprint: bridge + habitat + engineering + observation (camera-free) + cryo bay.

- One designed voyage arc (~90 minutes of player experience): wake → watch → charge → first jump → coast → a small crisis (hull ping / power pressure) → cryosleep → wake to her journal.

- A0 v2 trained on transcripts harvested from real slice sessions (the §12 Phase 1.x corpus loop, now fed by the actual game).

- Polish gate: §4.8 privacy audit (zero outbound calls), failure ladder (§4.7) exercised, save/load torture pass.

- Target: internal "Long Watch" demo build, December 19, 2026.

2027 H1 — public surface

- Q1: Steam page + GitHub release packaging + HF bundle (sysprompt + A0 LoRA); closed playtest circle (5–10 people, the Aurora/Solaris audience); Narrator-LLM in-engine for journal/universe texture.

- Targets: public demo (Steam) end of Q1 2027; Early Access or 1.0-lite decision mid-2027 based on playtest residue. Book vols 2–3 re-enter here as launch-adjacent material (Ship's Manual doubles as in-game codex).

### 8.3 Timeline confidence

| Milestone | Date | Confidence | Dominant uncertainty |
| --- | --- | --- | --- |
| Cycle close (gates + v0.129 + A0 go) | Jun 22 | 90% | operator availability only |
| A0 v1 evaluated | Jul 20 | 75% | trace-gen review cycles; one retrain |
| Vertical slice (Phase 2.0) | Aug 31 | 65% | E2 interop reality; first-engine-month friction |
| Warp month complete | Oct 15 | 60% | DX12↔CUDA shared-texture path; perf budget |
| Long Watch demo | Dec 19 | 55% | content breadth; the unknown-unknowns of "it's a game now" |
| Public demo | end Q1 2027 | 60% | Steam process + playtest findings |

A 55–65% on the big rocks is honest, not pessimistic: the multipliers are already in the dates. The pattern that protects the schedule: testbed-first (already done for E3/E4), contract-first (the two-adapter merge), and the bench as a regression net under every engine change.

### 8.4 What would accelerate the curve

- A second GPU box (or standing RunPod reservation) so training/eval never competes with the dev machine.

- A standing weekly 2-hour operator "senses block" — the queue of eyes/ears/judgment gates is the program's only real serialization point.

- CI runner (GitHub Actions, Windows) for the bench + nexus on every push — removes "did the harness run the gates?" trust entirely.

- A small closed playtest circle recruited before the demo exists (December gets much more valuable with five outside nervous systems).

## 9. Velocity & Estimation Basis (receipts)

What one operator + frontier-LLM harness measurably produced, recent cycle:

| Artifact | Wall-clock | Notes |
| --- | --- | --- |
| Visual testbed v0.1.0 (12 scenes, CUDA+GL, 119-check CI) | ~1 overnight autonomous session | checkpointed v5→v10 |
| UE 5.7 audio PoC (zero-asset, 5-layer DSP, voyage+WAV) | ~½ day incl. two toolchain root-causes | first UE module of the program |
| Bench Phase-0.x closure (SaveFile v3, 3 ephemerals, somatic, docs, +8 scenarios; +161 tests) | ~1 day autonomous run | 7 commits, ledger-driven, crash-tolerant |
| Audit + 4×1M-token discovery passes + v0.129 draft | ~1 day | the methodology now in AUDIT_METHODOLOGY.md |
| Book vol 1 (45.7K words, 4 print/digital formats, KDP submission) | ~2 days | separate session lineage |

The estimation rule used in §8.2: bench/tooling/docs tasks at measured velocity; anything touching UE5 editor/runtime at ×1.5–2 until two engine sprints calibrate the real coefficient. The §15.8 independent-track rule is what makes parallelism real rather than aspirational: tracks couple only at five named surfaces, so harness sessions in different tracks don't contend.

## 10. Operating Principles That Are Empirically Working

- Spec as envelope, code as residue (§15.4/§15.5). Two full cycles now where implementation findings — not speculation — drove every spec-change candidate. Mode 6 has been successfully starved.

- Testbed-before-engine. E3/E4 were de-risked as standalone artifacts with their own CI before UE5 work begins; UE5 inherits reference renders and reference WAVs, not vibes.

- Ledger-driven autonomy. Backups → honest resume ledger → one commit per unit → gates before and after → memory pinned. Today's run survived its own author's error modes because the structure caught them.

- Carve-out discipline. Python stays in the instrument; the product stays compiled. The boundary has held under pressure multiple times.

- Verify by artifact. Exit codes, summaries, and narratives are untrusted; DLLs, summary lines, diffs, and remote heads are the truth.

- Canon hygiene with named overloads. "STAGE" and "REEL" carry both project-local and canonical-protocol meanings; the collision is now documented at every use site rather than silently drifting.

## Appendix A — Repository Map (post-push, b3fa3b1)

C:\ASTRA-7\
  CLAUDE.md                      canon design document (read first)
  BOOTSTRAP.md                   fresh-session bootstrap procedure
  PROGRAM_STATUS_AND_ROADMAP_2026-06-10.md   ← this document
  AUTONOMOUS_RUN_2026-06-10.md   crash-tolerant run ledger (pattern reference)
  AUDIT_2026-05-15.md            architectural conformance audit
  DISCOVERY_2026-05-15*.md       4 parallel discovery passes
  *_PLAN_*.md / PROPOSAL_*.md / *DEEPDIVE*.md   research layer
  docs/
    spec-v0.128.md               CANON envelope
    spec-v0.129-tentative-*.md   pinned draft, finalization due
    stage-protocol.md            I/O grammar as implemented (DRAFT v0.1)
    narrator-spec.md             §6.4 implemented subset (DRAFT v0.1)
    AUDIT_METHODOLOGY.md         6-pass method + lessons L1–L4
    astra-sysprompt.md           ASTRA persona canon
  proto/
    astra_nexus.cpp / .exe       physics core, 71/71, LOCKED (additive only)
    textverse/                   the bench (Python carve-out) — 749 tests
  ASTRA_VISUALIZER_02/           visual testbed v0.1.0 (SHIPPED; S05 pending)
  ASTRA_VISUALIZER/              superseded V1 (source record)
  ASTRA_AUDIO/                   UE 5.7 warp-audio PoC (ear-pass pending)
  astra-a0-bootstrap/            fine-tune bootstrap (awaits GO)
  brainstorm/                    design consults (avionics, ensemble, dataset, sound)
  book/                          The Long Watch vol 1 + canon + negative_space
  .backups/                      local snapshots (gitignored)

## Appendix B — Gate Commands (the trust anchors)

# Bench (canonical runner)
cd C:\ASTRA-7\proto\textverse
"C:\Program Files\Python313\python.exe" -m uv run pytest -q     # 749 passed
"C:\Program Files\Python313\python.exe" -m uv run ruff check astra/ tests/
"C:\Program Files\Python313\python.exe" -m uv run mypy astra/   # strict

# Physics core
C:\ASTRA-7\proto\astra_nexus.exe                                # 71/71 + voyage table

# Visual testbed CI
ASTRA_VISUALIZER_02\tools\ci.bat                                # 12 scenes, golden diff

# Audio PoC build
"C:\Program Files\Epic Games\UE_5.7\Engine\Build\BatchFiles\Build.bat" ^
  AstraAudioEditor Win64 Development -Project="C:\ASTRA-7\ASTRA_AUDIO\AstraAudio.uproject"

## Appendix C — Key Numbers (2026-06-10)

| Metric | Value |
| --- | --- |
| Bench tests | 749 (588 at day start; +161 today) |
| Physics assertions (C++) | 71/71 |
| Visualizer scenes / assertions / golden diff | 12/12 · 44/44 · 0.0000 |
| Scenario library | 20 (entropy ceiling 4.32 bits) |
| Sculptor research log | 108 entries; baseline 1.6001; 4 promotes |
| Spec | v0.128 canon · v0.129 TENTATIVE (765 lines) |
| Commits pushed today | 13 (8 backlog + 5 custody) |
| Repo head (local == remote) | b3fa3b1 |
| Sysprompt-only persona ceilings (measured) | ~50% always-think · 12.5% bracket leak |
| A0 targets | ≥95% always-think · ≈0% leak |
| Hardware target | RTX 5090 rec / 4090 min · Win11+DX12 · Linux x86_64 secondary |

## Appendix D — Glossary & Name-Overload Warnings

- LCP — Loop Closure Property: the 9 measurable gates that define "the bench is really closed-loop."

- STAGE (two meanings!) — ASTRA-7-local: the LLM I/O grammar (think/tool/speech/silence). Canonical (Bo Chen, CC-BY-4.0, 2026-02-18): persona-agnostic world-input protocol ([scene]/[state]/[narration]/ [action]). See docs/stage-protocol.md §collision note.

- REEL (two meanings!) — ASTRA-7-local: ASTRA's memory log (≈ the canonical protocol's Tape). Canonical: the 5-ring memory architecture + Tape + 7 operations. Reconciliation is an open design thread.

- QC1/QC3 — enforced self-opacity / irreversibility-marking (spec §11 QUALIA-1 backbone).

- Calculator-bound (§15.6) — no LLM in the system ever computes a number; numerics come from deterministic tools and are validated at the boundary.

- Dave-frame — she knows she's an AI with a ship-body; she never learns about the player/PC meta-layer.

- Sculptor — the autonomous research loop that proposes → measures → promotes/falsifies bundle changes against the bench.

- A0 — ASTRA's first LoRA (K0-pipeline lineage, Scope γ).

## Appendix E — Cross-Canon Pointers (outside this repo)

- Canonical STAGE/REEL protocol specs: C:\BC_Canon\MAY2026\Deeper\

- K0 fine-tune pipeline (A0's template): C:\katherine-k0-finetune\

- PIY paper (silence/initiation architecture; future ASTRA presence work): C:\Users\user\Desktop\PIY_Paper_v2.md

- Inside The Region (tenancy/harness book; §9.3 dual-loop): C:\Inside_The_Region\

Prepared 2026-06-10 by the AI harness from verified state. The roadmap is the harness's sharpest current recommendation; the operator's adoption, amendment, or rejection of it is the next entry in the record.